## Decode Tasks
ID | DATE | YEAR | DECODE MONTH | ASSIGNED PERSON | ACTIVITY | STATUS | REMINDER SENT
1 | 2025-12-06 | 2026 | January | Rashid | Rashid sends list to Network Pathologists | Pending | No
10 | 2026-01-03 | 2026 | February | Rashid | Rashid sends list to Network Pathologists | Pending | No
2 | 2026-01-17 | 2026 | January | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
4 | 2026-01-26 | 2026 | January | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
3 | 2026-01-27 | 2026 | January | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
5 | 2026-01-31 | 2026 | January | Pathology Team | CHILD Decode | Pending | No
19 | 2026-01-31 | 2026 | March | Rashid | Rashid sends list to Network Pathologists | Pending | No
6 | 2026-02-02 | 2026 | January | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
7 | 2026-02-05 | 2026 | January | Rashid | Consensus Form sent | Pending | No
8 | 2026-02-07 | 2026 | January | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
9 | 2026-02-07 | 2026 | January | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
11 | 2026-02-14 | 2026 | February | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
13 | 2026-02-23 | 2026 | February | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
12 | 2026-02-24 | 2026 | February | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
14 | 2026-02-28 | 2026 | February | Pathology Team | CHILD Decode | Pending | No
28 | 2026-02-28 | 2026 | April | Rashid | Rashid sends list to Network Pathologists | Pending | No
15 | 2026-03-02 | 2026 | February | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
16 | 2026-03-05 | 2026 | February | Rashid | Consensus Form sent | Pending | No
17 | 2026-03-07 | 2026 | February | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
18 | 2026-03-07 | 2026 | February | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
20 | 2026-03-14 | 2026 | March | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
22 | 2026-03-23 | 2026 | March | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
21 | 2026-03-24 | 2026 | March | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
23 | 2026-03-28 | 2026 | March | Pathology Team | CHILD Decode | Pending | No
24 | 2026-03-30 | 2026 | March | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
25 | 2026-04-02 | 2026 | March | Rashid | Consensus Form sent | Pending | No
37 | 2026-04-04 | 2026 | May | Rashid | Rashid sends list to Network Pathologists | Pending | No
27 | 2026-04-04 | 2026 | March | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
26 | 2026-04-04 | 2026 | March | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
29 | 2026-04-11 | 2026 | April | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
31 | 2026-04-20 | 2026 | April | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
30 | 2026-04-21 | 2026 | April | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
32 | 2026-04-25 | 2026 | April | Pathology Team | CHILD Decode | Pending | No
33 | 2026-04-27 | 2026 | April | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
34 | 2026-04-30 | 2026 | April | Rashid | Consensus Form sent | Pending | No
35 | 2026-05-02 | 2026 | April | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
36 | 2026-05-02 | 2026 | April | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
46 | 2026-05-02 | 2026 | June | Rashid | Rashid sends list to Network Pathologists | Pending | No
38 | 2026-05-16 | 2026 | May | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
40 | 2026-05-25 | 2026 | May | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
39 | 2026-05-26 | 2026 | May | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
41 | 2026-05-30 | 2026 | May | Pathology Team | CHILD Decode | Pending | No
55 | 2026-05-30 | 2026 | July | Rashid | Rashid sends list to Network Pathologists | Pending | No
42 | 2026-06-01 | 2026 | May | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
43 | 2026-06-04 | 2026 | May | Rashid | Consensus Form sent | Pending | No
44 | 2026-06-06 | 2026 | May | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
45 | 2026-06-06 | 2026 | May | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
47 | 2026-06-13 | 2026 | June | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
49 | 2026-06-22 | 2026 | June | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
48 | 2026-06-23 | 2026 | June | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
50 | 2026-06-27 | 2026 | June | Pathology Team | CHILD Decode | Pending | No
51 | 2026-06-29 | 2026 | June | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
52 | 2026-07-02 | 2026 | June | Rashid | Consensus Form sent | Pending | No
64 | 2026-07-04 | 2026 | August | Rashid | Rashid sends list to Network Pathologists | Pending | No
54 | 2026-07-04 | 2026 | June | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
53 | 2026-07-04 | 2026 | June | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
56 | 2026-07-11 | 2026 | July | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
58 | 2026-07-20 | 2026 | July | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
57 | 2026-07-21 | 2026 | July | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
59 | 2026-07-25 | 2026 | July | Pathology Team | CHILD Decode | Pending | No
60 | 2026-07-27 | 2026 | July | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
61 | 2026-07-30 | 2026 | July | Rashid | Consensus Form sent | Pending | No
62 | 2026-08-01 | 2026 | July | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
63 | 2026-08-01 | 2026 | July | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
73 | 2026-08-01 | 2026 | September | Rashid | Rashid sends list to Network Pathologists | Pending | No
65 | 2026-08-15 | 2026 | August | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
67 | 2026-08-24 | 2026 | August | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
66 | 2026-08-25 | 2026 | August | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
68 | 2026-08-29 | 2026 | August | Pathology Team | CHILD Decode | Pending | No
69 | 2026-08-31 | 2026 | August | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
70 | 2026-09-03 | 2026 | August | Rashid | Consensus Form sent | Pending | No
82 | 2026-09-05 | 2026 | October | Rashid | Rashid sends list to Network Pathologists | Pending | No
71 | 2026-09-05 | 2026 | August | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
72 | 2026-09-05 | 2026 | August | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
74 | 2026-09-12 | 2026 | September | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
76 | 2026-09-21 | 2026 | September | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
75 | 2026-09-22 | 2026 | September | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
77 | 2026-09-26 | 2026 | September | Pathology Team | CHILD Decode | Pending | No
78 | 2026-09-28 | 2026 | September | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
79 | 2026-10-01 | 2026 | September | Rashid | Consensus Form sent | Pending | No
80 | 2026-10-03 | 2026 | September | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
91 | 2026-10-03 | 2026 | November | Rashid | Rashid sends list to Network Pathologists | Pending | No
81 | 2026-10-03 | 2026 | September | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
83 | 2026-10-17 | 2026 | October | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
85 | 2026-10-26 | 2026 | October | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
84 | 2026-10-27 | 2026 | October | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
100 | 2026-10-31 | 2026 | December | Rashid | Rashid sends list to Network Pathologists | Pending | No
86 | 2026-10-31 | 2026 | October | Pathology Team | CHILD Decode | Pending | No
87 | 2026-11-02 | 2026 | October | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
88 | 2026-11-05 | 2026 | October | Rashid | Consensus Form sent | Pending | No
90 | 2026-11-07 | 2026 | October | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
89 | 2026-11-07 | 2026 | October | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
92 | 2026-11-14 | 2026 | November | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
94 | 2026-11-23 | 2026 | November | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
93 | 2026-11-24 | 2026 | November | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
95 | 2026-11-28 | 2026 | November | Pathology Team | CHILD Decode | Pending | No
96 | 2026-11-30 | 2026 | November | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
97 | 2026-12-03 | 2026 | November | Rashid | Consensus Form sent | Pending | No
98 | 2026-12-05 | 2026 | November | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
99 | 2026-12-05 | 2026 | November | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No
101 | 2026-12-12 | 2026 | December | Drs. Andrew/Aziz | Case packets sent to SMEs | Pending | No
103 | 2026-12-21 | 2026 | December | Drs. Andrew/Aziz | Stakeholder memo sent for Dr. Ike's signature | Pending | No
102 | 2026-12-22 | 2026 | December | Rashid / Dr. Andrew / Aziz / Seyi | SMEs submit Decode Reports | Pending | No
104 | 2026-12-26 | 2026 | December | Pathology Team | CHILD Decode | Pending | No
105 | 2026-12-28 | 2026 | December | Drs. Andrew/Aziz/Bassey | Service Completion Certificate sent | Pending | No
106 | 2026-12-31 | 2026 | December | Rashid | Consensus Form sent | Pending | No
107 | 2027-01-02 | 2026 | December | Drs. Andrew/Aziz | Upload Decode Report to REDCap | Pending | No
108 | 2027-01-02 | 2026 | December | Drs. Andrew/Aziz | Send Decode Results to Surveillance | Pending | No